## Sheet1
Organization | Project | Country | Year | Budget | Budget (USD) | Reason for Failure | Structured Reason | Risk Category | Effect of Failure | Category of Impact
AMR, Marriott, Hilton | Confirm Project | USA | 1988 | $125M | 125000000 | Poor stakeholder involvement and Insufficient technical planning | Poor planning and Stakeholder issues | Strategic & Operational | Cancellation, legal disputes | Financial & Reputational
NZ Ministry of Education | Novopay | New Zealand | 2012 | NZD 182M | 108921053 | Poor stakeholder communication and Inadequate testing | Communication issues and Testing issues | Strategic & Operational | Payroll chaos, user dissatisfaction | Financial & Reputational
UK Home Office | E-Borders Programme | UK | 2003 | £830M | 1105057850 | Overambitious scope and Weak governance | Scope issues and Weak governance | Strategic & Compliance | Delays, wasted funds | Financial & Operational
California DMV | CA DMV IT Modernization | USA | 1988 | $44M | 44000000 | Insufficient technical planning & Lack of oversight | Poor planning and Vendor issues | Operational | Cancellation, wasted funds | Financial
Netflix | Netflix Qwikster | USA | 2011 | N/A | N/A | Poor stakeholder consideration and Poor communication | Communication issues and Stakeholder issues | Strategic & Financial | Subscriber loss, $12B market cap drop | Financial & Reputational
Microsoft | Windows RT | USA | 2012 | N/A | N/A | Misjudged market demand and Poor requirements analysis | Market misjudgment and Requirements issues | Strategic | Product failure, revenue loss | Financial
Sony | Sony PSN Outage | Japan | 2011 | N/A | N/A | Cybersecurity oversight and Lack of contingency planning | Contingency planning issues and Vendor issues | Compliance & Operational | Data breach, service shutdown | Financial & Reputational
FBI | FBI VCF Project | USA | 2000 | $170M | 170000000 | Scope creep; Weak governance and Poor requirements | Scope issues and Weak governance | Strategic & Operational | Project failure, delayed modernization | Financial & Operational
City of Denver | Denver Baggage System | USA | 1995 | $560M | 560000000 | Insufficient technical planning and Overambitious scope | Poor planning and Scope issues | Strategic & Operational | Delays, abandonment | Financial & Operational
BBC | BBC DMI | UK | 2008 | £98M | 122500000 | Poor stakeholder involvement and Weak governance | Stakeholder issues and Weak governance | Strategic & Operational | Cancellation, reputational damage | Financial & Reputational
National Health Service (NHS) | NHS NPfIT | UK | 2002 | £12.7B | 16904933043 | Poor stakeholder involvement, Weak governance, and Overambitious scope | Scope issues, Stakeholder issues, and Weak governance | Strategic & Operational | Project dismantled, loss of funds | Financial & Operational
Airbus | Airbus A380 Wiring Issue | France | 2006 | N/A | N/A | Insufficient technical planning and Poor coordination across teams | Coordination issues and Poor planning | Strategic & Operational | Production delays, cost overruns | Financial & Reputational
Boeing | Boeing 737 MAX | USA | 2018 | N.A | N/A | Inadequate risk disclosure and Poor safety testing | Risk management issues and Testing issues | Compliance & Operational | Grounding of fleet, reputational crisis | Financial & Reputational
IBM / Texas Government | IBM Project for State of Texas | USA | 2006 | $863M | 863000000 | Poor vendor oversight and Inadequate requirements clarity | Requirements issues and Vendor issues | Strategic & Operational | Contract termination, operational failures | Financial & Operational
Sydney Water Corporation | Sydney Water ERP Project | Australia | 2002 | AUD 61M | 39650000 | Poor requirements definition and Inadequate stakeholder input | Requirements issues and Stakeholder issues | Strategic & Operational | Budget blowout, staff resistance | Financial & Reputational
London Stock Exchange | TAURUS Stock Settlement System | UK | 1980s | £800M+ | 1000000000 | Overambitious scope and Poor planning and coordination | Poor planning and Scope issues | Strategic & Operational | Abandonment after years of dev | Financial
UK Home Office | Her Majesty’s Passport Office IT Project | UK | 2014 | £385M | 481250000 | Poor stakeholder involvement and Weak governance | Stakeholder issues and Weak governance | Strategic & Operational | System delays, travel disruptions | Financial & Operational
LAS | London Ambulance Service CAD System | UK | 1992 | £1.5M | 1875000 | Inadequate technical testing and Poor contingency planning | Contingency planning issues and Testing issues | Operational | System crash, emergency delays | Operational & Reputational
Target Corp. | Target Canada Expansion IT Setup | Canada | 2013 | $7B (total) | 7000000000 | Poor data migration and Weak supplier coordination | Data issues and Vendor issues | Strategic & Operational | Store closures, $5.4B loss | Financial
Lidl (Germany) | SAP Implementation | Germany | 2011 | €500M | 540000000 | Overambitious scope and Poor customization strategy | Customization issues and Scope issues | Strategic & Operational | Abandonment of system | Financial
iSoft / NHS | iSoft Lorenzo System (NHS) | UK | 2003 | £12B | 15977580000 | Incomplete system readiness and Misaligned expectations | Expectation misalignment and Readiness issues | Strategic & Operational | Clinical data risks, user rejection | Operational & Reputational
NParks | Singapore NParks Ride Tracking System | Singapore | 2015 | SGD 600K | 457280 | Poor vendor oversight and Compliance breaches | Compliance issues and Vendor issues | Compliance & Operational | Audit failure, contract penalties | Financial
NHS England | Care.data Program | UK | 2013 | £8M+ | 10000000 | Poor communication and Low public/stakeholder trust | Communication issues and Trust issues | Compliance & Strategic | Project suspended, trust erosion | Reputational
Montclair State University | Oracle ERP Failure at Montclair State Univ. | USA | 2009 | $20M | 20000000 | Poor vendor governance and Requirements mismatch | Requirements issues and Weak governance | Operational & Financial | Legal disputes, overruns | Financial & Reputational
Australian Energy Market Operator | Smart Metering System | Australia | 2011 | 2.4B AUD | 1538532000 | Poor stakeholder coordination and Insufficient integration testing | Stakeholder issues and Testing issues | Strategic & Operational | Delays, user dissatisfaction | Financial & Operational
British Airways | Heathrow Terminal 5 Baggage System | UK | 2008 | £250M | 312500000 | Insufficient technical testing and Poor contingency planning | Contingency planning issues and Testing issues | Operational | Delays, baggage chaos | Financial & Reputational
City of New York | NYC CityTime Payroll System | USA | 2003 | $700M | 700000000 | Vendor fraud and Weak governance | Fraud and Weak governance | Compliance & Financial | Criminal charges, fund recovery issues | Financial & Legal
Rolls-Royce | Rolls-Royce Trent 1000 Engine Mgmt | UK | 2016 | N/A | N/A | Inadequate risk forecasting and Design flaw oversight | Design issues, Risk management issues, and Vendor issues | Strategic & Operational | Global aircraft grounding | Operational & Reputational
Indian Railways | Computerisation of the Indian Railways | India | 1985 | N/A | N/A | Poor stakeholder involvement and Weak integration strategy | Integration issues and Stakeholder issues | Strategic & Operational | Project delays, public dissatisfaction | Operational
U.S. Internal Revenue Service | IRS CADE 2 Modernization | USA | 2009 | $1B+ | 1000000000 | Scope creep and Poor vendor coordination | Scope issues | Strategic & Operational | Delays in full deployment | Financial
Victorian Government | Myki Smartcard System | Australia | 2005 | AUD 1.5B | 975000000 | Inadequate vendor management and Integration failures | Integration issues and Vendor issues | Operational & Financial | Overruns, long delays | Financial & Reputational
UK DWP | UK Universal Credit Program (early phases) | UK | 2013 | £15.8B (total program) | 19750000000 | Poor scope control and Weak agile planning | Poor Planning and Scope issues | Strategic & Operational | Public backlash, waste | Financial & Reputational
CA DMV | California DMV IT Overhaul (Redux) | USA | 2018 | $135M | 135000000 | Repeated operational mismanagement and Legacy tech risk | Operational management issues | Operational | Delays, inefficiencies | Operational
Hawaii State Govt. | Hawaii Health Connector | USA | 2013 | $205M | 205000000 | Vendor failure and Inadequate integration testing | Testing issues | Operational & Financial | Site unusable, federal takeover | Financial & Compliance
U.S. Coast Guard | US Coast Guard Deepwater IT/Comms Upgrade | USA | 2002 | $24B | 24000000000 | Weak oversight and Poor risk governance | Vendor issues and Weak governance | Strategic & Compliance | Contract cancellation, tech gaps | Financial & Operational
State of Colorado | Colorado Benefits Management System (CBMS) | USA | 2004 | $200M+ | 200000000 | Poor stakeholder training and Weak vendor coordination | Stakeholder issues | Operational | Application errors, public backlash | Reputational
U.S. Federal Government | IBM HealthCare.gov Backend | USA | 2013 | $800M+ | 800000000 | Insufficient integration testing and Poor oversight | Testing issues and Vendor issues | Strategic & Operational | National outage, political scrutiny | Financial & Reputational
French Military | France's Louvois Military Payroll System | France | 2011 | €470M | 507600000 | Inaccurate data handling and Poor risk response plan | Risk response Issues | Operational & Financial | Missed payments, system shutdown | Financial
U.S. Air Force | US Air Force Expeditionary Combat Support System (ECSS) | USA | 2005 | $1B+ | 1000000000 | Overambitious scope and Weak project control | Scope issues | Strategic | Total failure, program cancelled | Financial
British Gas | British Gas SAP CRM System | UK | 2006 | £40M | 50000000 | Inadequate testing and Poor change management | Testing issues | Operational | Billing issues, customer complaints | Reputational
Ontario Ministry of Health | Ontario eHealth Project | Canada | 2008 | 1B CAD | 723761824 | Weak governance and Poor vendor oversight | Vendor issues and Weak governance | Strategic & Financial | Public scandal, resignations | Financial & Political
Passport Canada | IBM’s Passport Canada System | Canada | 2007 | 100M CAD | 72368500 | Poor requirements gathering and Integration issues | Requirement Issues and Integration Issues | Strategic & Operational | Long delays, public dissatisfaction | Operational
NZ Police / IBM | New Zealand Police INCIS Project | New Zealand | 1990s | 104M NZD | 62246562 | Incomplete planning and Mismanaged stakeholder input | Stakeholder issues | Strategic & Operational | Project abandonment | Financial
Australian Gov. | Australia’s Robodebt System | Australia | 2016 | 1.5B AUD | 9615000005 | Compliance failure and Poor data validation | Compliance issues | Compliance | Lawsuits, refunds, political fallout | Financial & Legal
California State | California Child Support Automation | USA | 1990s | $1B+ | 1000000000 | Poor project governance and Scope creep | Scope issues and Weak governance | Strategic | Legal risks, massive delays | Financial & Legal
IRS | IRS Modernized e-File System (early phase) | USA | 2004 | $1B | 1000000000 | Legacy system conflicts and Poor vendor coordination | Legacy system Issues and Vendor Issues | Operational | Years of delay | Operational
UK DWP | DWP Pension Reform IT (UK) | UK | 2015 | £100M+ | 125000000 | Misaligned agile planning and Weak inter-agency collaboration | Poor planning and collaboration Issues | Strategic | Program halted | Financial
Thai Government | Thailand’s Smart ID Card Rollout | Thailand | 2014 | N/A | N/A | Weak public awareness and Compliance issues | Compliance issues | Compliance & Operational | Poor adoption, wasted resources | Reputational
Danish National Police | Denmark Police System POLSAG | Denmark | 2007 | DKK 500M+ | 70000000 | Requirements mismatch and Vendor failure | Requirements issues | Operational | System abandoned | Financial
Florida State | IBM’s Unemployment Insurance Modernization (Florida) | USA | 2009 | $77M | 77000000 | Poor change control and Inadequate user testing | Testing issues | Operational | Site crashes, payment delays | Financial & Reputational